SOFTWARE PROJECT PLAN

Project Plan: Scope, Timeline and Team Roles

Sample application: QuickBite – Online Food Ordering System

1. Aim

To prepare a software project plan covering the scope, timeline and team roles for a sample application, so that the work can be organised, estimated and tracked before development starts.

2. Project Overview

QuickBite is a web and mobile-friendly application that lets customers browse restaurants, order food, pay online and track order status. Restaurants manage menus and incoming orders, and an administrator oversees users, restaurants and reports.

| Item | Details |
| --- | --- |
| Project name | QuickBite – Online Food Ordering System |
| Objective | Deliver a working food ordering platform for one city within 12 weeks. |
| Development model | Iterative-incremental with two-week sprints (six sprints). |
| Technology stack | React (frontend), Node.js + Express (backend), MySQL (database), Razorpay test gateway (payments), Git/GitHub. |
| Team size | 5 members |

3. Scope

| In scope | Out of scope |
| --- | --- |
| User registration and login (customer, restaurant, admin) | Native Android/iOS apps |
| Restaurant listing, search and menu browsing | Live GPS rider tracking and delivery-partner app |
| Cart, checkout and online payment (test mode) | Real-money payment settlement |
| Order placement, status updates and order history | AI-based recommendations |
| Restaurant dashboard to manage menu and orders | Multi-city and multi-language support |
| Admin panel with basic reports | Third-party marketing integrations |

Deliverables: Software Requirements Specification (SRS), design documents (UML and ER diagram), working application, test report, user manual and final presentation.

Assumptions and constraints: fixed 12-week schedule; a payment gateway in test mode only; team members are part-time students; hosting limited to a free-tier cloud service.

4. Timeline and Milestones

The project is planned over 12 weeks. The chart below shows when each task runs (shaded weeks); overlapping tasks are done by different team members in parallel.

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Requirements & SRS |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. System design (UML, DB) |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. UI/UX prototype |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Backend development |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Frontend development |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Integration & payments |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Testing & bug fixing |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Deployment & handover |  |  |  |  |  |  |  |  |  |  |  |  |

| Milestone | Due | Completion criteria |
| --- | --- | --- |
| M1: SRS approved | End of Week 2 | Requirements signed off by the guide. |
| M2: Design complete | End of Week 4 | UML diagrams, ER diagram and UI prototype reviewed. |
| M3: Core features | End of Week 8 | Login, menu, cart and order placement working. |
| M4: Feature complete | End of Week 10 | Payments and dashboards integrated. |
| M5: Release | End of Week 12 | All test cases pass; app deployed; documents submitted. |

5. Team Roles and Responsibilities

| Role | Members | Responsibilities |
| --- | --- | --- |
| Project Manager | 1 | Plan and schedule, assign tasks, track progress, run weekly reviews, manage risks. |
| Business / Requirements Analyst | 1 | Gather requirements, write SRS and user stories, prepare the user manual. |
| Backend Developer | 1 | Design the database and REST APIs, authentication, payment integration. |
| Frontend / UI Developer | 1 | Build the UI/UX prototype and responsive screens, connect them to the APIs. |
| QA / Test Engineer | 1 | Write test plan and cases, run functional and regression tests, log defects, handle deployment checks. |

Note: in a 5-person team every member also reviews others’ code through GitHub pull requests, and all members share documentation work.

6. Risk Management

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Requirements change mid-project | High | Medium | Change-control log; sprint-wise review with the guide. |
| Schedule slips due to exams or part-time availability | High | High | Buffer in Weeks 11–12; prioritise must-have features. |
| Payment gateway integration problems | Medium | High | Start integration early; use test mode and mock fallback. |
| Team member unavailable | Medium | Medium | Pair work and shared repository so tasks can be taken over. |
| Defects found late | Medium | High | Test during every sprint instead of only at the end. |

7. Monitoring and Tools

- Progress tracking: GitHub Projects board (To do / In progress / Done) and a 15-minute weekly stand-up.

- Version control: GitHub with feature branches and pull-request reviews.

- Communication: WhatsApp/Teams group; weekly status report to the guide.

8. Conclusion

The plan defines a bounded scope, a 12-week schedule with five milestones and clear role ownership. Managing the listed risks, especially schedule slippage and changing requirements, is the key to delivering QuickBite on time.